## Sheet1
Count of Key | Column Labels
Row Labels | Awaiting for Dev | Not Started | Done on Pre | WIP on Beta | Done on Beta | Not for QA | Grand Total
(blank)
RMM | 25 |  | 6 | 1 | 1 | 2 | 35
ACCT | 2 | [5 empty] | 2
OSS | 3 | [5 empty] | 3
VAULT | 2 | 1 | 1 |  |  |  | 4
MGMT | 2 | [5 empty] | 2
DC | 1 | [5 empty] | 1
Grand Total | 35 | 1 | 7 | 1 | 1 | 2 | 47

## general_report
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date | Fix Version/s | QA Estimate | QA time remaining | Testing Status | QA Owner | Parent Jira ID
Bug | RMM | Issue while adding user in Active directory | Md Jiaul Islam | Kavita More | Average | Needs Info | Unresolved | 2014-04-15 08:03 | 2014-06-27 02:21 |  | 2014.07 |  |  |  | Sanket Sawant
Bug | RMM | Change in Script name "Continuum Malwarebytes uninstallation". | Kavita More | Abhishek Tiwaskar | Average | Needs Info | Unresolved | 2014-05-27 09:12 | 2014-06-26 03:28 |  | 2014.07
New Feature | ACCT | TerminationNotice - Locked partners. | Deepak Chouksey | Accounting group per Pramod | Average | Resolved | Fixed | 2014-04-25 11:42 | 2014-06-24 04:29 |  | 2014.07
Improvement | OSS | Enhance the automatic retrieval of credentials when connecting to a LMI Machine | Deepak Chouksey | Dustin Weber | Average | Resolved | Fixed | 2014-05-30 10:22 | 2014-06-27 07:48 |  | 2014.07S
New Feature | RMM | Synchronize MDM data to ConnectWise | Ramesh Tulluri | Risa Barnett | Average | Resolved | Fixed | 2012-10-02 13:58 | 2014-06-24 03:12 |  | 2014.04, 2014.06, 2014.07 |  |  | Done on Pre | Ramesh Tulluri
Improvement | RMM | Connectwise API ITS-Setup UI work | Yamini Panchal | Amory Wakefield | Average | Resolved | Fixed | 2013-05-24 16:07 | 2014-06-24 03:13 |  | 2014.06, 2014.07 |  |  | WIP on Beta | Yamini Panchal
Bug | RMM | Ticket prefixes pushing ticket e-mail subject line over ConnectWise character limit | Vipul Nikam | Matt Talarczyk | Minor | Resolved | Fixed | 2013-05-14 13:08 | 2014-06-26 02:04 |  | 2014.06, 2014.07 |  |  | Done on Pre | Vipul Nikam
Improvement | RMM | Synchronize Linux servers to ConnectWise | Ramesh Tulluri | Risa Barnett | Average | Resolved | Fixed | 2013-08-28 10:27 | 2014-06-24 03:14 |  | 2014.04, 2014.07 |  |  | Done on Pre | Ramesh Tulluri
Task | RMM | Pass "cw-app-id" = "continuum" cookie with ConnectWise integrations | Dheeraj Namdeo | Risa Barnett | Average | Resolved | Fixed | 2013-09-09 17:05 | 2014-06-24 03:14 |  | 2014.04, 2014.07
Improvement | RMM | Comprehensive PSA synchronization monitoring for ConnectWise | Vipul Nikam | Louise Simonds | Critical | Resolved | Fixed | 2013-11-12 17:07 | 2014-06-24 03:16 | 2014-03-15 | 2014.04, 2014.07 |  |  | Done on Pre | Vipul Nikam
New Feature | RMM | Connectwise API Integration : Site synchronization & mapping | Yamini Panchal | Dheeraj Namdeo | Average | Resolved | Fixed | 2014-01-09 06:43 | 2014-06-24 03:17 |  | 2014.04, 2014.07 |  |  |  | Yamini Panchal
Bug | RMM | Missing Warranty information on new Executive Summary reports | Anilkumar Chippa | Shah Alam | Average | Resolved | Fixed | 2014-01-27 16:09 | 2014-06-27 02:52 |  | 2014.07 | 6.9 | 6.9 |  | Anilkumar Chippa
Bug | RMM | Warranty Information shows 0 in SPF+ Monthly Report | Anilkumar Chippa | Shah Alam | Average | Resolved | Fixed | 2014-01-27 16:16 | 2014-06-27 02:52 |  | 2014.07 | 6.9 | 6.9 |  | Anilkumar Chippa
Task | RMM | Connectwise API - Migration of Tickets for Existing Partner | Arun Panoli | Jaspal Khanna | Average | Resolved | Fixed | 2014-02-14 01:48 | 2014-06-24 03:17 |  | 2014.04, 2014.06, 2014.07 |  |  | Done on Pre | Vipul Nikam
Improvement | RMM | Executive Report Colors - need updated | Zaid Qureshi | Shauna Peters | Average | Resolved | Fixed | 2014-02-17 09:06 | 2014-06-27 04:16 |  | 2014.07 | 5.943 | 5.943 |  | Anilkumar Chippa
Improvement | RMM | Graph color changes | Radhey Sarode | midatlantic team | Average | Resolved | Fixed | 2014-03-05 13:41 | 2014-06-25 23:28 |  | 2014.07 | 4.256 | 4.256 |  | Anilkumar Chippa
Improvement | RMM | Reports Color Change Bar Graph | Zaid Qureshi | Tonya Barnett | Average | Resolved | Fixed | 2014-03-12 11:05 | 2014-06-27 04:19 |  | 2014.07 | 4.256 | 4.256 |  | Anilkumar Chippa
Improvement | RMM | Connectwise API - Enable Maintenance button | Vipul Nikam | Jaspal Khanna | Average | Resolved | Fixed | 2014-05-23 12:48 | 2014-06-24 03:17 |  | 2014.06, 2014.07 |  |  | Done on Pre | Vipul Nikam
Task | RMM | Agent Deployment Tool setup creation - June-2014 | Bilal Khan | Bilal Khan | Average | Resolved | Fixed | 2014-06-02 04:58 | 2014-06-24 10:43 |  | 2014.06, 2014.07 |  |  | Not for QA | Neeta Gaikwad
Bug | RMM | When creating a Site Admin, 'Yes' to create sites doesn't take me anywhere. | Deepak Chouksey | Lisa Daly | Minor | Resolved | Fixed | 2014-06-05 10:34 | 2014-06-27 08:09 |  | 2014.07
Bug | RMM | Getting error while trying view Starter Package form details from Ticket Screen in NOC Portal | Deepak Chouksey | Ajay Vernekar | Average | Resolved | Fixed | 2014-06-10 12:05 | 2014-06-26 03:59 |  | 2014.07
Improvement | RMM | Update needed for help text on the "Assign Default Communicator" page | Bilal Khan | Lisa Daly | Minor | Resolved | Fixed | 2014-06-17 09:00 | 2014-06-26 04:31 |  | 2014.07
Bug | RMM | Getting error when we try to configure Partner-defined-vmware policies. | Deepak Chouksey | Vinay Soni | Critical | Resolved | Fixed | 2014-06-17 08:31 | 2014-06-23 04:34 |  | 2014.07
Bug | RMM | Reboot error message on patching deployment policy is incorrect | Mohammed Asif Qureshi | Amory Wakefield | Minor | Resolved | Fixed | 2014-06-19 09:51 | 2014-06-27 08:40 |  | 2014.07 |  |  |  | Mohammed Asif Qureshi
Improvement | RMM | Change Communicator opt-in text | Bilal Khan | Lisa Daly | Average | Resolved | Fixed | 2014-06-20 10:57 | 2014-06-26 08:32 |  | 2014.07
Improvement | RMM | Change "Assign Default Communicator" tab | Bilal Khan | Lisa Daly | Trivial | Resolved | Fixed | 2014-06-20 11:03 | 2014-06-26 04:28 |  | 2014.07
New Feature | VAULT | Include Vault data in ConnectWise synchronization | Ramesh Tulluri | Risa Barnett | Average | Resolved | Fixed | 2013-03-08 09:26 | 2014-06-24 03:13 |  | 2013.06, 2014.04, 2014.07 |  |  | Done on Pre | Ramesh Tulluri
Improvement | VAULT | Enable RT form for NOC and TAMs | Ranu Tiwari | Jeff Neumann | Average | Resolved | Fixed | 2014-04-23 11:02 | 2014-06-27 04:27 |  | 2014.07 |  |  | Not Started | Ranu Tiwari
Improvement | RMM | Add Formatting modules to Executive Reports redesign | Pradeep Bhosale | Risa Barnett | Average | Reopened | Unresolved | 2013-12-11 16:41 | 2014-06-24 11:30 |  | 2014.07 | 4.41 | 0 | Done on Beta | Zaid Qureshi
Improvement | ACCT | Automated the Monthly Billing Process for MSO , AV , Vault | Manasi Salvi | Krishnakant Verma | Average | In Progress | Unresolved | 2014-03-25 03:20 | 2014-06-18 08:33 |  | 2014.07
Task | DC | Remote Viewer access model needs to be rethought to address non-repudiation issue | Farhad Variava | Nick Bruno | Critical | In Progress | Unresolved | 2014-02-26 03:14 | 2014-06-19 08:57 |  | 2014.07
Improvement | MGMT | Search feature for Click Thru Report and Bypass Tool | Srabani Mohanty | Sagar Salot | Average | In Progress | Unresolved | 2014-06-23 01:07 | 2014-06-27 03:16 |  | 2014.07
Bug | OSS | Multiple Tickets genenerated through Application for Agent Self heal. | Chandrakant Singh | Chandrakant Singh | Critical | In Progress | Unresolved | 2014-06-18 03:13 | 2014-06-26 06:19 |  | 2014.07S
Improvement | RMM | Move VMware/vCenter setup from Devices to Agent | Nitin Kumar | southwest team | Average | In Progress | Unresolved | 2013-04-04 15:03 | 2014-06-26 03:45 |  | 2014.07
Bug | RMM | Unable to auto update Remote Agent Deployment IP Scanner tool | Ganesh Sankpal | Ganesh Jain | Average | In Progress | Unresolved | 2014-04-23 20:42 | 2014-06-24 11:36 |  | 2014.06, 2014.07 |  |  | Not for QA | Neeta Gaikwad
Improvement | RMM | Change Vault Offsite storage database object that feeds Connectwise and Autotask. | Arvind Kumar | Jeff Neumann | Critical | In Progress | Unresolved | 2014-05-09 16:00 | 2014-06-17 01:27 |  | 2014.07
Bug | RMM | Continuum Communicator - Character limitation | Kavita More | Vishal Rane | Average | In Progress | Unresolved | 2014-06-25 14:46 | 2014-06-26 03:13 | 2014-07-23 | 2014.07
Improvement | VAULT | Vault orders provisioned after July 1 to use Total Dataset for offsite billing | Arvind Kumar | Jeff Neumann | Average | In Progress | Unresolved | 2014-05-23 00:20 | 2014-06-17 01:26 |  | 2014.07
Improvement | MGMT | Add SD Enabled Date to "Service Desk Disable" emails | Nitin Kumar | Joel Kennedy | Average | Open | Unresolved | 2014-05-01 12:30 | 2014-06-26 03:12 |  | 2014.07
Bug | OSS | Error while taking LMI throught TicketID. | Yogesh Pawar | Anwar Ali Ansari | Critical | Open | Unresolved | 2014-05-30 09:09 | 2014-06-27 08:21 |  | 2014.07S
Bug | RMM | Use of scroll bars on Setup > Devices makes screen difficult to read | Mahesh Chalke | Jen Roadman | Minor | Open | Unresolved | 2014-05-29 12:00 | 2014-06-26 03:23 |  | 2014.07
Bug | RMM | Count mismatch in Tickets tab on ITS portal - View Alerts by Status (NOC Defined & Managed Alerts) | Joicy Noby | Joicy Noby | Average | Open | Unresolved | 2014-05-30 04:31 | 2014-06-26 03:31 |  | 2014.07
Bug | RMM | MalwareBytes Installed Status | Joicy Noby | Amit Mehta | Average | Open | Unresolved | 2014-06-02 13:20 | 2014-06-26 03:22 |  | 2014.07
Task | RMM | Need to remove junk xml from patch failuer parshing process | Sukhvinder Singh | Roopali Pandey | Average | Open | Unresolved | 2014-06-03 01:55 | 2014-06-27 07:57 |  | 2014.07 |  |  |  | Mohammed Asif Qureshi
Bug | RMM | Malwarebytes Quick Scan gets over written if opted out. | Joicy Noby | Ankit Garg | Average | Open | Unresolved | 2014-05-21 20:47 | 2014-06-26 03:24 |  | 2014.07
Bug | RMM | Patches Home Tooltip contain incorrect failure information | Nitin Kumar | Zulfikar Shaikh | Minor | Open | Unresolved | 2014-06-20 07:53 | 2014-06-27 07:57 |  | 2014.07 |  |  |  | Mohammed Asif Qureshi
Bug | VAULT | Quick Access shows Vault if they don't have a Vault | Jigar Parekh | midatlantic team | Average | Open | Unresolved | 2014-06-18 10:52 | 2014-06-26 03:21 |  | 2014.07
Generated at Fri Jun 27 08:46:26 EDT 2014 by Benazir Sayyad using JIRA 6.3-OD-07-013#6327-sha1:66bf7cb9930e9269cff96498083bad782dab4617.